## Slide 1
TURNAROUND & SHUTDOWN MANAGEMENT SYSTEM
Work-Pack Generation Process
A Technical Process Note on How SYORITY Builds Job-Wise Turnaround Work-Packs
Prepared for Gujarat Narmada Valley Fertilizers & Chemicals Limited (GNFC)
Annual Shutdown 2027 — Bharuch, Gujarat | Tender Ref: GNFC/TS/ASD-2027/SCHEDULING
Prepared by Syority Corporation Pvt. Ltd. | 19 August 2026

## Slide 2
PURPOSE
Why This Note, and What a Work-Pack Delivers
This note responds to GNFC's question on how Syority will generate the ~30 job-wise Turnaround work-packs required under Annexure-I. It sets out the process, the team, the timeline, and how each element GNFC has specified is produced.
A SYORITY work-pack is a fully structured, equipment-specific job package covering everything a discipline engineer, QA/QC inspector and site supervisor needs — from job scope and isolation through inspection, repair, box-up and final sign-off.
Traditional Excel-Based Method | SYORITY Structured Process | Impact for GNFC TA 2027
8 – 14 days to assemble one work-pack manually | 10 – 16 hours per work-pack using templates + AI-assisted extraction | ~30 work-packs engineered well within the Oct 2026 – TA start window
Drawing data re-typed by hand into spreadsheets | AI Vision/OCR reads P&IDs, GA drawings & nozzle schedules; planner verifies | Fewer transcription errors in nozzle, gasket & bolting data
Work-pack content scattered across files, inconsistent format | Single standardized template per equipment class; all fields captured | Consistent, auditable work-packs across all disciplines
SYORITY — Work-Pack Generation Process | GNFC Annual Shutdown 2027
2

## Slide 3
OPERATING PHILOSOPHY
Human Engineering Authority, AI-Assisted Speed
The planning engineer retains 100% engineering authority over every work-pack. AI is used in exactly one place — reading drawings and extracting structured data — and every value it produces is verified by a qualified planner before it becomes part of the record.
AI's ROLE
Bounded & Non-Destructive
High-speed computer vision / OCR scanning of P&IDs, GA drawings, nozzle schedules, isometrics & vendor data sheets.
Extraction of structured candidate data: equipment tags, design pressure/temperature, nozzle sizes, bolting, gasket type.
AI never finalizes a work-pack, assigns resources, or approves a certificate.
PLANNER'S ROLE
100% Engineering Authority
Verifies every AI-extracted value against the source drawing before it is accepted.
Builds the plant/equipment hierarchy and instantiates work-packs from standardized templates.
Assigns crew resources, sequences activities, defines hold points, and sets durations.
Generates and signs off statutory quality certificates; manages schedule and reporting dashboards.
SYORITY — Work-Pack Generation Process | GNFC Annual Shutdown 2027
3

## Slide 4
PROGRAMME CONTEXT
Where Work-Pack Generation Sits in the TA Lifecycle
Work-pack generation is Phase 2 of the five-phase SYORITY turnaround lifecycle. Its output feeds the master CPM schedule (Phase 3), field progress tracking (Phase 4) and the as-built closeout dossier (Phase 5).
PHASE 1
Drawing & Data
Ingestion
▶
PHASE 2
Work-Pack & QA
Engineering
▶
PHASE 3
Scheduling, CPM
& P6 Export
▶
PHASE 4
Execution &
Progress (DPR)
▶
PHASE 5
Closeout &
Reporting
The remainder of this deck focuses on Phase 2 — how each individual work-pack is actually built.
SYORITY — Work-Pack Generation Process | GNFC Annual Shutdown 2027
4

## Slide 5
WORK-PACK GENERATION PROCESS
Step by Step (1 of 2)
1
Master Asset Hierarchy Setup
Build the plant hierarchy: Enterprise/Client → Site → Complex/Plant → Unit → System → Equipment, with every asset tagged by equipment classification.
2
Drawing Upload & AI-Assisted Data Extraction
AI Vision/OCR reads P&IDs, GA drawings, nozzle schedules & data sheets to produce a structured candidate record — equipment tag, design data, nozzles, bolting, gasket type. The only AI touchpoint in the process.
3
Planner Verification & Master Data Commitment
A qualified planner verifies every extracted value against the source drawing before it is committed to the Equipment Technical Record, Joint Integrity Register & Blind Register.
SYORITY — Work-Pack Generation Process | GNFC Annual Shutdown 2027
5

## Slide 6
WORK-PACK GENERATION PROCESS
Step by Step (2 of 2)
4
Template Selection from the Canonical Activity Library
The planner selects the standard template matching the equipment and job (e.g. HX-BUNDLE-INSP), built from 102 standardized activity codes across 14 families.
5
Automated Template Instantiation
Instantiation auto-populates standard operations, logic links, crew allocations, QA/QC hold points and quantity fields; the planner then fine-tunes durations, resources and materials to the specific job.
6
Attaching QA/QC Forms, Checklists & Statutory Certificates
Flange box-up & torquing certificate, pressure test certificate, box-up clearance checklist, blind tracker — each pre-formatted with the required multi-stage sign-off.
SYORITY — Work-Pack Generation Process | GNFC Annual Shutdown 2027
6

## Slide 7
DEPLOYMENT TEAM
GNFC TA 2027 — Work-Pack Engineering Core
A focused two-person core team mobilizes from October 2026, operating within the broader manpower mobilization required under Annexure-I Section 6.
Execution Expert
Min. 5 – 8 years
Brings hands-on plant turnaround / field execution experience — realistic isolation sequencing, known failure modes, practical repair scope, safety & permit considerations, lessons from prior shutdowns.
Planner
Min. 5 years
Owns the SYORITY structured database — builds the equipment hierarchy, verifies drawing extraction, instantiates & fine-tunes templates, sets durations/resources/logic links, develops the CPM schedule.
How the two roles work together
For each piece of equipment, the Execution Expert provides field-tested input on scope, isolation and repair extent; the Planner converts this — together with AI-verified drawing data — into a structured work-pack in SYORITY, sequencing activities, assigning resources and attaching certificates.
SYORITY — Work-Pack Generation Process | GNFC Annual Shutdown 2027
7

## Slide 8
WORK-PACK STRUCTURE
Anatomy of a SYORITY Work-Pack — 11 Standard Sections
Sec. | Title | Content
A | Cover Page | WO reference, equipment tag, unit, scope summary, approval sign-off
B | Revision Page | Revision history — number, date, description, planner
C | Work-Pack Content | Table of contents + full attachment index
D | Scope Definition | Equipment description, specifications, scope narrative
E | Operations | Core activity table — exported to Primavera P6 / MS Project
F | Division of Responsibility | GNFC vs. Contractor responsibility matrix
G | Hold/Witness — Asset Integrity | QA/QC gates signed off by client Asset Integrity
H | Hold/Witness — Tech. Services | QA/QC gates signed off by Technical Services / NDT
I | Electrical Requirements | Power, lighting & electrical equipment needed
J | Consumables / Materials | Itemized material list with quantities
K | Blind / Isolation Checklist | Certification of every mechanical isolation
SYORITY — Work-Pack Generation Process | GNFC Annual Shutdown 2027
8

## Slide 9
QA/QC DISCIPLINE
Hold Points vs. Witness Points
 | Hold Point | Witness Point
Definition | Work must stop until the designated inspector arrives, inspects and signs off. | Inspector should be present to observe, but work may proceed if unavailable after due notice.
Implication | Mandatory gate — the downstream activity is logically blocked until cleared. | Advisory — must be documented, but does not block the schedule.
Typical examples | Pre-cleaning inspection, NDT/thickness survey, tube-sheet inspection, DFT/holiday testing, box-up inspection. | Pneumatic test, hydrotest, water-fill/UV leak test.
Standard Attachment Groups
Attachment 1 — Drawings & Technical Information: marked-up P&ID, detail drawings, isometrics, equipment data sheet.
Attachment 2 — Formats & Certificates: cleaning acceptance, scaffolding, box-up, flange-joint & torquing checklists, job completion certificate, lessons-learnt format.
Attachment 3 — Plans & Procedures: Level-IV schedule, JSA, standard maintenance procedure, inspection procedure, method statement, lifting plan (where applicable).
SYORITY — Work-Pack Generation Process | GNFC Annual Shutdown 2027
9

## Slide 10
STANDARDIZATION
The Canonical Activity Library — 102 Activities, 14 Families
Family | Code | Examples
Preparation | PREP | Scaffolding, insulation removal, lighting
Isolation | ISO | Blind install, vent/drain, lock-out
Dismantling | DISMANTLE | Channel/shell cover, tube bundle removal
Cleaning | CLEAN | HP water jet, chemical clean, hydro-blast
Inspection | INSP | Visual internal, tube internal, shell thickness
NDT | NDT | ECT, IRIS, MPI, UT gauging, PAUT
Repair & Maintenance | REPAIR | Tube plugging, weld overlay, facing
Family | Code | Examples
Surface Treatment | SURFACE | Blasting, primer coat, top coat
Assembly & Box-Up | ASSY | Bundle insert, shell cover, torquing
Testing | TEST | Shell hydro, tube hydro, pneumatic test
Quality Control | QC | Final box-up sign-off, punch clearance
Hold Points | HP | Statutory inspection, box-up clearance
Logistics & Crane | LOGISTICS | Crane setup, bundle transport
Administration | ADMIN | Permit to work, toolbox talk
Every equipment-class template draws its standard operations from this library — a typical heat-exchanger bundle inspection pre-populates ~47 operations with 13 QA/QC hold points.
SYORITY — Work-Pack Generation Process | GNFC Annual Shutdown 2027
10

## Slide 11
TRACEABILITY
Mapping to GNFC's Annexure-I Work-Pack Requirements
Annexure-I Requirement | How SYORITY Generates It
Job scope definition | Captured at template instantiation, refined by the planner (header/description block)
Equipment details / Nozzle list / Manholes / Gaskets | Populated from the verified Equipment Technical Record & drawing extraction (Steps 2–3)
Thickness data | Recorded from drawing extraction; updated with field UT survey results during execution
Isolation & cleaning steps | Standard ISO/CLEAN-family activities auto-populated by the template engine
Inspection tasks / Repair plan | Standard INSP/NDT/REPAIR-family activities, quantified against inspection findings
Material list / Manpower / Duration | Compiled and fine-tuned by the planner during template instantiation (Step 5)
Logical sequencing & dependencies | Predecessor/successor logic auto-mapped, feeding the CPM schedule
Required resources & constraints | Set during template fine-tuning; tracked through execution
SYORITY — Work-Pack Generation Process | GNFC Annual Shutdown 2027
11

## Slide 12
PROGRAMME TIMELINE
October 2026 to TA Closeout
Oct'26
Nov'26
Dec'26
Jan'27
Feb'27
Mar'27
Apr'27
May'27
Activity
Requirement Gathering
Format & Attachment Workflow
Work-Pack Development (~30 nos.)
Scheduling / CPM (baseline @ T-15)
TA Execution Support (39 ± 5 days)
Closeout Report (15 days post-TA)
Baseline schedule reviewed with GNFC and frozen at T-15 days before the tentative first-week-of-April 2027 TA start. Closeout dossier delivered within 15 days of TA completion.
SYORITY — Work-Pack Generation Process | GNFC Annual Shutdown 2027
12

## Slide 13
SCHEDULING INTEGRATION
From Work-Pack to Master Schedule
Once a work-pack's activities, durations, sequencing and resources are finalized, it feeds directly into the master integrated TA schedule. SYORITY's native forward/backward-pass CPM engine links every work-pack's activities into the plant-wide network, calculates critical-path status in real time, and surfaces float at both the activity and work-pack level.
Primavera P6 XER
Full WBS hierarchy, TASK & TASKPRED, UDFTYPE 9 mapped (SY_ACTIVITY_CODE)
Primavera P6 XML
Schema-validated API business object, exact logic links
MS Project XML
FieldID extended attribute mappings, task hierarchy, custom attributes
Exportable in Primavera P6 (XER & XML) and MS Project (XML) formats — for direct use in GNFC's own project systems, exactly as called for in Annexure-I.
SYORITY — Work-Pack Generation Process | GNFC Annual Shutdown 2027
13

## Slide 14
PRODUCTIVITY
Effort & Productivity Benchmarks
Activity | Manual / Excel | SYORITY Process
Work-pack assembly (per work-pack) | 8 – 14 days | 10 – 16 hours
Drawing data extraction | ~4 hours manual typing | ~2 minutes AI scan + planner review
Quality hold-point bypasses | 5% – 8% missed in field | 0% — system-enforced logic lock
DPR / progress compilation | 3 – 4 hours every evening | 1-click automated DPR
For GNFC's scope of ~30 job-wise work-packs, at 10–16 engineering hours per work-pack this is well within the capacity of the two-person core team across the three-month Work-Pack Development window (Dec 2026 – Feb 2027).
SYORITY — Work-Pack Generation Process | GNFC Annual Shutdown 2027
14

## Slide 15
DELIVERABLES
Resulting Deliverables for GNFC TA 2027
Detailed job-wise work-packs (approx. 30 nos.) covering job scope, equipment details, nozzle list, manholes, gaskets, thickness data, isolation, cleaning, inspection, repair plan, materials, manpower & duration estimation, and logical sequencing.
Integrated master TA schedule in Primavera P6 / MS Project format, with all work-packs linked and critical path identified.
Baseline and periodically updated schedules through the Pre-TA and execution phases.
Daily and weekly progress reports, and 1-day/3-day/7-day look-ahead schedules during the 39-day execution window.
Final as-built schedule and TA close-out report, including the digital work-pack dossier.
Continued software access for a minimum of 5 years, including 3 years of secure online access to as-built work-pack records for future shutdown baselining.
SYORITY — Work-Pack Generation Process | GNFC Annual Shutdown 2027
15

## Slide 16
Speed From Standardization.
Judgement From Human Engineers.
A dedicated Execution Expert and Planner will take GNFC's ~30 job-wise work-packs through requirement gathering, format finalization, structured development and scheduling across six months from October 2026 — with a fully baselined schedule at T-15 days before the tentative April 2027 TA start, and the closeout dossier within 15 days of completion.
Syority Corporation Pvt. Ltd. remains available to walk GNFC's technical services team through a live demonstration of this process, including sample work-packs.
Thank You